## Dashboard
FootPath Cebu — Project Management Dashboard
Integrating Athletic Development & Academic Eligibility Tracking for Grassroots Youth Football
Project KPI Summary
| Metric | Count | Status
| Total Project Tasks | 78 | On Track
| Completed Tasks | 6
| In Progress Tasks | 14
| Not Started Tasks | 58
| Project Leader and Head Planner | Ralf Andre Ebuna - overall project planning, coordination, architecture, and milestone oversight | Project Head
Project Leadership and Team Assignments
| Team Member | Leadership and Primary Project Focus | Assigned Tasks
| Ralf Andre Ebuna | Project Leader and Head Planner. Lead Full-Stack Developer for mobile, cybersecurity, authentication, and synchronization. | 28
| Rhobert C. Patena | Full-Stack Developer for Django APIs, Supabase architecture, staff eligibility, and administrative workflows. | 26
| Reiner Seldon C. Dela Cerna | Frontend and QA Engineer for Flutter MVVM interfaces, Guardian and Scout portals, and automated testing. | 24
Member Color Legend
| Ralf Andre Ebuna | Project Leader and Head Planner
| Rhobert C. Patena | Django and Supabase development
| Reiner Seldon C. Dela Cerna | Frontend and quality assurance
| ALL MEMBERS | Shared team responsibility

## Project WBS
WBS Code | Task/Deliverable Description | Assignee / Phase Lead | Start Date | End Date | Status | % Complete | Phase / Module
1 | PHASE 1: PROJECT LEADERSHIP, RESEARCH, SYSTEM ARCHITECTURE & DESIGN | Ralf Andre Ebuna (Project Leader) | 2026-07-06 | 2026-07-12 | Completed | 100% | Planning & Design
1.1 | Requirements Refinement & Must-Haves Alignment | Ralf Andre Ebuna | 2026-07-06 | 2026-07-08 | Completed | 100% | Planning & Design
1.1.1 | Map out 5 specialized user roles (Admin, Coach, Scout, School Staff, Player) | Ralf Andre Ebuna | 2026-07-06 | 2026-07-07 | Completed | 100% | Planning & Design
1.1.2 | Define structural logic for 3 age tiers (Foundation, Development, Pathway) | Rhobert C. Patena | 2026-07-07 | 2026-07-08 | Completed | 100% | Planning & Design
1.2 | Database & Security Architecture Design | Ralf Andre Ebuna | 2026-07-08 | 2026-07-12 | Completed | 100% | Planning & Design
1.2.1 | Design Firebase/Firestore schema avoiding raw grades storage (flag-only eligibility) | Ralf Andre Ebuna | 2026-07-08 | 2026-07-10 | Completed | 100% | Planning & Design
1.2.2 | Formulate offline-first caching policy and Firestore replication schemas | Ralf Andre Ebuna | 2026-07-09 | 2026-07-11 | Completed | 100% | Planning & Design
1.2.3 | Establish JWT/Firebase rule-based access control (RBAC) definitions | Reiner Seldon C. Dela Cerna | 2026-07-10 | 2026-07-12 | Completed | 100% | Planning & Design
2 | PHASE 2: CORE FRAMEWORK & 50% MILESTONE DEVELOPMENT | Ralf Andre Ebuna (Project Leader) | 2026-07-13 | 2026-08-04 | In Progress | 45% | 50% Core Development
2.1 | Authentication & Role-Based Access Control (RBAC) |  | 2026-07-13 | 2026-07-18 | Completed | 100% | 50% Core Development
2.1.1 | Implement Firebase-authenticated login for all 5 roles | Ralf Andre Ebuna | 2026-07-13 | 2026-07-15 | Completed | 100% | 50% Core Development
2.1.2 | Enforce strict block on public self-registration (Admin-issued credentials only) | Ralf Andre Ebuna | 2026-07-16 | 2026-07-18 | Completed | 100% | 50% Core Development
2.2 | Admin Control Panel (Core Features) |  | 2026-07-19 | 2026-07-24 | In Progress | 70% | 50% Core Development
2.2.1 | Develop User Provisioning engine (create accounts & link Guardian-to-Player) | Ralf Andre Ebuna | 2026-07-19 | 2026-07-22 | In Progress | 90% | 50% Core Development
2.2.2 | Build age-tier settings configuration UI (Foundation, Development, Pathway) | Reiner Seldon C. Dela Cerna | 2026-07-22 | 2026-07-24 | In Progress | 50% | 50% Core Development
2.3 | Coach Module — Schedules & Attendance Foundation |  | 2026-07-25 | 2026-07-31 | In Progress | 30% | 50% Core Development
2.3.1 | Create Training Schedule calendar management UI | Reiner Seldon C. Dela Cerna | 2026-07-25 | 2026-07-28 | In Progress | 60% | 50% Core Development
2.3.2 | Implement offline-first local SQLite/Hive data capture layer for attendance | Ralf Andre Ebuna | 2026-07-27 | 2026-07-30 | In Progress | 20% | 50% Core Development
2.3.3 | Build attendance radio toggles (Present, Absent, Excused) with automatic sync | Ralf Andre Ebuna | 2026-07-29 | 2026-07-31 | In Progress | 10% | 50% Core Development
2.4 | Coach Rubric & Ratings Engine |  | 2026-07-28 | 2026-08-02 | In Progress | 20% | 50% Core Development
2.4.1 | Build standardized 1-10 rating rubric form matrices | Reiner Seldon C. Dela Cerna | 2026-07-28 | 2026-07-30 | In Progress | 40% | 50% Core Development
2.4.2 | Implement position-aware custom criteria fields vs goalkeeper variants | Ralf Andre Ebuna | 2026-07-30 | 2026-08-01 | Not Started | 0% | 50% Core Development
2.4.3 | Develop qualitative feedback text logs capture | Ralf Andre Ebuna | 2026-08-01 | 2026-08-02 | Not Started | 0% | 50% Core Development
2.5 | Academic Eligibility Gating & School Staff Interface |  | 2026-07-30 | 2026-08-03 | In Progress | 15% | 50% Core Development
2.5.1 | Build School Staff status panel (Eligible, Not Eligible, Pending, Academic Warning) | Ralf Andre Ebuna | 2026-07-30 | 2026-08-01 | In Progress | 30% | 50% Core Development
2.5.2 | Enforce grade isolation logic (never store raw grades, status flag driven only) | Ralf Andre Ebuna | 2026-08-01 | 2026-08-02 | Not Started | 0% | 50% Core Development
2.5.3 | Implement basic status tracking history log for connected players | Ralf Andre Ebuna | 2026-08-02 | 2026-08-03 | Not Started | 0% | 50% Core Development
2.6 | Player & Guardian Portal Foundation |  | 2026-08-01 | 2026-08-04 | Not Started | 0% | 50% Core Development
2.6.1 | Develop Player profile visualization view (position, age tier, active attributes) | Reiner Seldon C. Dela Cerna | 2026-08-01 | 2026-08-03 | Not Started | 0% | 50% Core Development
2.6.2 | Build Guardian multi-child linkage switcher dashboard | Reiner Seldon C. Dela Cerna | 2026-08-02 | 2026-08-04 | Not Started | 0% | 50% Core Development
2.6.3 | Create read-only mirror views for child attendance, metrics, and schedule | Ralf Andre Ebuna | 2026-08-03 | 2026-08-04 | Not Started | 0% | 50% Core Development
M1 | 50% MILESTONE DEFENSE EVALUATION (CRITICAL MILESTONE) | ALL MEMBERS | 2026-08-05 | 2026-08-05 | Not Started | 0% | Milestone Defense
3 | PHASE 3: ADVANCED MUST-HAVES & SYSTEM INTEGRATION (POST-50%) | Ralf Andre Ebuna (Project Leader) | 2026-08-06 | 2026-10-25 | Not Started | 0% | 100% Post-50% Dev
3.1 | Scout Discovery Module |  | 2026-08-06 | 2026-08-25 | Not Started | 0% | 100% Post-50% Dev
3.1.1 | Build permissioned Discovery Interface dashboard for grassroots players | Reiner Seldon C. Dela Cerna | 2026-08-06 | 2026-08-12 | Not Started | 0% | 100% Post-50% Dev
3.1.2 | Develop extensive multi-parameter filtering/search (age tier, position, ratings) | Rhobert C. Patena | 2026-08-13 | 2026-08-18 | Not Started | 0% | 100% Post-50% Dev
3.1.3 | Build 'Scouted Players Master List' tracking system & save features | Reiner Seldon C. Dela Cerna | 2026-08-19 | 2026-08-22 | Not Started | 0% | 100% Post-50% Dev
3.1.4 | Implement Player Data Transfer / Referral Request initiation engine | Ralf Andre Ebuna | 2026-08-21 | 2026-08-25 | Not Started | 0% | 100% Post-50% Dev
3.2 | Guardian Consent Workflow & Data Transfer Control |  | 2026-08-26 | 2026-09-10 | Not Started | 0% | 100% Post-50% Dev
3.2.1 | Create Guardian interactive screen to review pending Scout referral requests | Reiner Seldon C. Dela Cerna | 2026-08-26 | 2026-09-02 | Not Started | 0% | 100% Post-50% Dev
3.2.2 | Build explicit Approve/Deny transaction handling for minor player profiles | Ralf Andre Ebuna | 2026-09-03 | 2026-09-07 | Not Started | 0% | 100% Post-50% Dev
3.2.3 | Implement secure cryptographic profile access token release post-consent | Ralf Andre Ebuna | 2026-09-07 | 2026-09-10 | Not Started | 0% | 100% Post-50% Dev
3.3 | Rule-Based Deterministic Recommendations Engine |  | 2026-09-11 | 2026-09-25 | Not Started | 0% | 100% Post-50% Dev
3.3.1 | Code backend logic parsing attendance %, academic standing, and rubrics | Rhobert C. Patena | 2026-09-11 | 2026-09-17 | Not Started | 0% | 100% Post-50% Dev
3.3.2 | Generate deterministic training recommendation tags based on algorithm | Ralf Andre Ebuna | 2026-09-18 | 2026-09-22 | Not Started | 0% | 100% Post-50% Dev
3.3.3 | Display recommendation alerts in Coach dashboard and Player profile view | Reiner Seldon C. Dela Cerna | 2026-09-22 | 2026-09-25 | Not Started | 0% | 100% Post-50% Dev
3.4 | Dispute Mechanism & System Audit Logging |  | 2026-09-26 | 2026-10-08 | Not Started | 0% | 100% Post-50% Dev
3.4.1 | Build Coach interface to flag/respond to eligibility or rating disputes | Reiner Seldon C. Dela Cerna | 2026-09-26 | 2026-09-30 | Not Started | 0% | 100% Post-50% Dev
3.4.2 | Develop School Staff participation portal inside the dispute flow | Rhobert C. Patena | 2026-10-01 | 2026-10-04 | Not Started | 0% | 100% Post-50% Dev
3.4.3 | Create Admin definitive review dashboard and immutable audit log repository | Ralf Andre Ebuna | 2026-10-04 | 2026-10-08 | Not Started | 0% | 100% Post-50% Dev
3.5 | Communication & Value-Add Systems |  | 2026-10-09 | 2026-10-25 | Not Started | 0% | 100% Post-50% Dev
3.5.1 | Integrate Firebase Cloud Messaging for Push Notifications (Schedule, Feedback, Eligibility) | Ralf Andre Ebuna | 2026-10-09 | 2026-10-14 | Not Started | 0% | 100% Post-50% Dev
3.5.2 | Build real-time In-app messaging gateway between Coaches and Guardians | Ralf Andre Ebuna | 2026-10-14 | 2026-10-19 | Not Started | 0% | 100% Post-50% Dev
3.5.3 | Develop PDF Export feature for printable reports, player digital cards, and statistics | Rhobert C. Patena | 2026-10-19 | 2026-10-22 | Not Started | 0% | 100% Post-50% Dev
3.5.4 | Create centralized Notification Center view with history for all roles | Reiner Seldon C. Dela Cerna | 2026-10-21 | 2026-10-25 | Not Started | 0% | 100% Post-50% Dev
4 | PHASE 4: INTEGRATED TESTING, SECURITY AUDIT & BUG FIXING | Ralf Andre Ebuna (Project Leader) | 2026-10-26 | 2026-11-10 | Not Started | 0% | Testing & QA
4.1 | Comprehensive Security & Role-Isolation Verification | Ralf Andre Ebuna | 2026-10-26 | 2026-10-31 | Not Started | 0% | Testing & QA
4.1.1 | Perform RBAC penetration test to verify zero grade leakage or unauthorized route access | Ralf Andre Ebuna | 2026-10-26 | 2026-10-28 | Not Started | 0% | Testing & QA
4.1.2 | Verify encryption protocols on Firestore database rules and sync channels | Rhobert C. Patena | 2026-10-29 | 2026-10-31 | Not Started | 0% | Testing & QA
4.2 | Functional, Offline & User Acceptance Testing (UAT) |  | 2026-11-01 | 2026-11-10 | Not Started | 0% | Testing & QA
4.2.1 | Conduct simulated offline-first edge testing (sudden disconnects during attendance logs) | Reiner Seldon C. Dela Cerna | 2026-11-01 | 2026-11-04 | Not Started | 0% | Testing & QA
4.2.2 | Execute complete lifecycle testing for player data referral from Scout to Guardian approval | Reiner Seldon C. Dela Cerna | 2026-11-04 | 2026-11-07 | Not Started | 0% | Testing & QA
4.2.3 | Fix performance bugs, layout regressions, and slow sync queries | ALL MEMBERS | 2026-11-07 | 2026-11-10 | Not Started | 0% | Testing & QA
5 | PHASE 5: DEPLOYMENT, OPTIMIZATION & FINAL DEFENSE PREPARATION | Ralf Andre Ebuna (Project Leader) | 2026-11-11 | 2026-11-17 | Not Started | 0% | Deployment
5.1 | Production Environment Setup & Launch |  | 2026-11-11 | 2026-11-15 | Not Started | 0% | Deployment
5.1.1 | Deploy live application to staging/production app distribution channels | Ralf Andre Ebuna | 2026-11-11 | 2026-11-13 | Not Started | 0% | Deployment
5.1.2 | Execute final database seeding with regional team entries and initial Admin keys | Rhobert C. Patena | 2026-11-13 | 2026-11-15 | Not Started | 0% | Deployment
5.2 | Final Presentation & 100% Milestone Milestone Defense Prep | ALL MEMBERS | 2026-11-15 | 2026-11-17 | Not Started | 0% | Deployment
M2 | 100% MILESTONE DEFENSE PRESENTATION (FINAL GRADUATION MILESTONE) | ALL MEMBERS | 2026-11-18 | 2026-11-18 | Not Started | 0% | Milestone Defense